## Sheet1
Recommendation | VRP Delivery Group | Progress |  |  | Latest Supporting Evidence
|  | 2023-05-01 | 2023-11-01 | 2024-02-01
1.1) A long-term plan should be developed to capture the roles and commitments of each Specified Authority to produce and regularly update the SNA, including expected contributions around provision of data, insight and analytical resource. | • Data and Analysis Working Group |  |  |  |  | • VRP SVD Agreement for Specified Authorities in draft, for sign off at SVRP (25/03/2024). • SVRP survey to also be published at next SVRP (25/03/2024).
1.2) Future SNA’s should draw on a broader range of data from partners to develop a fuller picture of serious violence. | • Data and Analysis Working Group |  |  |  |  | • Partnership Data Tracker created to monitor all data sources.
2.1) Partners should consider existing work being done by the central VRU and the former ‘spoke’ VRU’s and incorporate a gaps analysis in the development of the strategy. | • Strategic Violence Reduction Partnership |  |  |  |  | • Crest Advisory workshops completed to discuss VRP Response Strategy. • The Strategy workshop and TVRP identified that the model change left a gap in smaller community based interventions. The Violence Reduction Fund grants round worked collaboratively with CSP managers to fund 15 interventions.
2.2) Ensure that the central VRU’s strategy covers the breath of the four local authority areas, and that partners jointly feed into the strategy development. | • Strategic Violence Reduction Partnership |  |  |  |  | • VRP Response Strategy now finalised and published to all partners via the VRP Strategy Launch, focusing on the four strategy objectives: - Multi-Agency Systems Change - Data and Analysis - Engagement and Communications - Intervention, Evaluations and Opportunities
3.1) As the response strategy is produced, HIPS should harness the collaborative development of the strategy to drive a consistent approach to evaluation and impact measurement. | • Interventions, Evaluations and Opportunities Working Group |  |  |  |  | • A consistent approach to evaluation and impact measurement is achieved through the VRP Outcomes Based Performance Framework (OBPF) and the VRP Commissioning and Evaluation Approach. The OBPF is grounded in the VRP Theory of Change (ToC), which was developed in collaboration with specified authorities. For more robust evaluation, the VRP Commissioning and Evaluation Approach is sufficiently high level and will be regularly referred to in the Interventions, Evaluation and Opportunities Working Group.
3.2) The partnership should develop a theory of change or similar structure to provide the basis for performance monitoring and evaluation. | • Data and Analysis Working Group |  |  |  |  | • The existing VRU level ToC was reviewed and refreshed to form a VRP level ToC which reflects the refreshed partnership arrangements. It uses the national VRU programme ToC as a template, but with the Hampshire & IOW VRP strategic objectives as captured in the VRP response strategy. All components are included with sustainability in mind. • An Outcomes Based Performance Framework (OBPF) has been created to maintain oversight of what the data suggests about the VRU's progress towards key success measures and trends. The framework is grounded in the VRU level ToC. The framework can evolve as new activity is realised, such as data sharing through Hampshire & IoW Together (HIOWT).
4.1) Set expectations with all specified authorities on what they are expected to contribute to the Duty. | • Strategic Violence Reduction Partnership |  |  |  |  | • VRP SVD Agreement for Specified Authorities in draft, for sign off at SVRP (25/03/2024).
4.2) Disseminate a centralised message to practitioners in each area, clearly defining the roles, responsibilities and remits under the Duty for each partner authority. | • Strategic Violence Reduction Partnership |  |  |  |  | • VRP Response Strategy now finalised and published to all partners via the VRP Strategy Launch. • Serious Violence Toolkit Launch held 19/03/2024, which sets out what each practitioner is required to do to meet the Duty. • VRP SVD Agreement for Specified Authorities in draft, for sign off at SVRP (25/03/2024).
5.1) The partnership should develop an engagement plan covering how children, young people and families will be consulted to inform the SNA and serious violence strategy, as well as the delivery of interventions. | • Engagement Working Group |  |  |  |  | • Delivery commenced via Engagement Working Group, in progress and under review.
5.2) This plan should set out how the partnership intend to reach diverse cohorts, and to research saturation / oversampling. | • Engagement Working Group |  |  |  |  | • Delivery commenced via Engagement Working Group, in progress and under review.
6.1) Partners should review data collection practices and ensure that there is a consistent approach to data collection. Actions to improve data collection and data quality should be identified by partners. | • Data and Analysis Working Group |  |  |  |  | • To be delivered via Hampshire and Isle of Wight Together (HIOWT) Working Group (once live) • HIOWT Implementation Board and SRO currently in place.
6.2) Current data sharing practices should be brought together within a unified framework, with an aim of reducing the reliance on individual Information Sharing Agreements, and aligning with expected contributions. | • Data and Analysis Working Group |  |  |  |  | • To be delivered via Hampshire and Isle of Wight Together (HIOWT) Working Group (once live) • HIOWT Implementation Board and SRO currently in place.
6.3) Training and information should be provided to partners on good data sharing principles and legal requirements around data sharing in connection within the Duty. The partnership should also hold a relationship-building data sharing workshop with partners, in order to work through the reticence around information sharing. | • Data and Analysis Working Group |  |  |  |  | • VRP Response Strategy now finalised for all strategic objectives, including Data and Analysis and published to all partners via the VRP Strategy Launch. • To be delivered via Hampshire and Isle of Wight Together (HIOWT) Working Group (once live) • Plan for Joint Information Governance, mirroring Thames Valley Together (TVT) approach.
7.1) Managers within each of the four VRU areas should consider supporting workforce development and training among local practitioners around the public health approach, to further operationalise the approach and provide clarity to frontline practitioners. | • VRU Work Programme: Priority 5 – VRU Manager Elle Snookes leading |  |  |  |  | • VRU Managers working with Local Safer Children's Partnership (LSCP) to create the Serious Violence Toolkit, which launched on 19/03/2024. • VRU Manager directly running Trauma Informed training to staff across the Local Authorities. • VRU Manager due to meet with National partners about their lead on the Public Health Approach, which will be taken to Interventions, Evaluations and Opportunities Working Group for further discussion and planning on 17/04/2024.
7.2) Partners should collaborate on best practice using the VRU’s connections with the Thames Valley area, considering what’s worked in Thames Valley from a public health perspective, and how these learning could be utilised in Hampshire and the Isle of Wight. | • Interventions, Evaluations and Opportunities Working Group |  |  |  |  | • Attendance at national and county wide events. • Engagement and delivery via partnership meetings / webinars / online surveys. • Engaged with TVP VRU and Thames Valley Together (TVT). HIOW VRU have attended numerous national events run by the HO / YEF and Ecorys. Close links with TVP VRU with joint projects such as HIOWT and Hotspot app (how officers record their hotspots).
7.3) Partners should place a focus on a public health model, in particular understanding the prevalence of risk factors and the effectiveness of universal prevention activity when developing and updating data and information sharing arrangements across the partnership and with commissioned services. | • Data and Analysis Working Group |  |  |  |  | • To be delivered via Hampshire and Isle of Wight Together (HIOWT) Working Group (once live)
8.1) Partners should invest in more comprehensive community mapping, to identify the individuals and organisations across Hampshire and the Isle of Wight that could be actively involved in violence reduction efforts. | • Engagement Working Group |  |  |  |  | • Delivery commenced via Engagement Working Group. Community mapping in progress.
8.2) Effective communication channels should be established to ensure that all partners are aware of existing community arrangements, including who is being targeted and what approach is being used. | • Tactical Violence Reduction Partnership |  |  |  |  | • Delivery commenced via TVRP Working Group. Through the TVRP, Police have identified cohorts at risk and bring CSP Managers together to work out what interventions are taking place with these individuals and how local provisions can support diversions.
8.3) Best practice should be shared among partners to facilitate collaboration when engaging with communities and to encourage the adoption of effective violence reduction techniques. | • Engagement Working Group |  |  |  |  | • Delivery commenced via Engagement Working Group.
Evidenced: Deliverables have been successfully achieved and the relevant objectives have been successful.
Current: Project objectives are being actively tracked and delivery is in progress, however cannot yet be fully demonstrated.
Outstanding: Project deliverables have yet to be fully scoped and / or product delivery has not been started.
Evidenced: Deliverables have been successfully achieved and the relevant objectives have been successful.
Current: Project objectives are being actively tracked and delivery is in progress, however cannot yet be fully demonstrated.
Outstanding: Project deliverables have yet to be fully scoped and / or product delivery has not been started.
Note on C2: Hamer, Mandeep (50661): Original readiness assessment completed by Crest Advisory.
Note on D2: Hamer, Mandeep (50661): Agreed and adopted by SVRP in Nov 2023
Note on E2: Hamer, Mandeep (50661): Progress reviewed by VRU Strategic Lead.